## Student Scopes
CDE4301 Capstone Team Roles & Individual Scopes
Each student is graded individually based on their specific, non-overlapping design & research deliverables.
Role / Owner | Technical Focus Subtopic | Key Semester 1 Progress Target | Key Semester 2 Deliverables
Student 1 (You) [Mechanical] | FOD Retrieval & Chassis Mechanical Design | Suck-up power calculations; dynamic model of MacPherson suspension; CAD layout of pneumatic vacuum hood and secondary physical sweep roller. | Fabrication of the hybrid pickup hood; chassis structural analysis (FEA); track validation of suspension ground-clearance (87mm - 116mm tolerance) over runway expansion joints.
Student 2 [Electrical] | Power Distribution & Actuation Systems | Sizing high-capacity LiPo battery arrays; power protection circuit diagram; ESC calibration for high-draw BLDC vacuum motor and drive motors. | Physical assembly of power distribution board (PDB); integration of safety isolation/emergency-stop switches; electrical efficiency and heat dissipation trials under continuous run.
Student 3 [Robotics Software] | UGV SLAM Navigation & Waypoint Follower | Configuring ROS2 navigation stack; runway mapping using lidar-based SLAM in simulation; drive-by-wire encoder interface design. | Autonomous UGV runway sweep algorithm; waypoint-following tracking stability tests; outdoor obstacle avoidance sensor integration; positioning drift evaluation.
Student 4 [Aerospace / UAV] | UAV Flight Operations & Optical Gimbal Payload | UAV drone flight controller setup; optical payload housing & camera gimbal mechanical layout; safety geo-fencing software definitions. | High-speed aerial scanning runs for FOD localization; reliable drone-landing platform integration; landing-gear locking triggers; wind-shear flight stabilization tests.
Student 5 [Computer Vision] | CV Detection Model & Multi-Agent Telemetry Bridge | YOLOv8 custom dataset annotations (M8 bolts, biological carcasses); drone-to-ground wireless telemetry network bridge setup (ROS2 web-bridge). | Real-time object classification and coordinates-to-waypoint transformation pipeline; communication latency analysis; edge-AI camera deployment and detection metrics (mAP > 92%).

## Gantt Chart
CDE4301 Capstone Year-Long Gantt Chart & Workflow
Chronological tracking of task progress across Semester 1 and Semester 2 (August 2026 - April 2027)
|  | Sem 1 W1 | Sem 1 W2 | Sem 1 W3 | Sem 1 W4 | Sem 1 W5 | Sem 1 W6 | SEM 1 RECESS WEEK | Sem 1 W7 | Sem 1 W8 | Sem 1 W9 | Sem 1 W10 | Sem 1 W11 | Sem 1 W12 | Sem 1 W13 | READING WEEK | EXAM WEEK 1 | EXAM WEEK 2 | VACATION WEEK 1 | VACATION WEEK 2 | VACATION WEEK 3 | VACATION WEEK 4 | Sem 2 W1 | Sem 2 W2 | Sem 2 W3 | Sem 2 W4 | Sem 2 W5 | Sem 2 W6 | Sem 2 Recess Week | Sem 2 W7 | Sem 2 W8 | Sem 2 W9 | Sem 2 W10 | Sem 2 W11 | Sem 2 W12 | Sem 2 W13
Student In Charge | Remarks | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
Asuka | Problem finding and Problem definition | Secondary research on problem |  |  |  | Primary Research on Problem |  | Finalise Problem Insight report and problem definition | [5 empty] | INTERRIM PRESENTATION: Critical Function Prototype | DOCCUMENTATION DUE ON THIS WEEK |  |  |  | RESERVIST | [14 empty] | FINAL DOCCUMENTATION DUE ON WEEK 11 |  | FINAL PRESENTATION
| Needs Defintion |  | Generation of List of Requirements and list of specifications |  |  | Purchase of items needed for CFP
| Vacuum Subsystem |  | Calculations and design for Vacuum Subsystem |  |  |  | Development of second design iteration | Fabrication of Vacuum Head | Testing of Vacuumm Subsystem | Improvement on Vacuum Susbsystem |  | Finalise Design for Vacuum subsystem
| Suspension Subsystem |  | Calculations and design for Suspension Subsytem |  |  |  | Waiting on component arrival | Fabrication of Suspension Brackets | Testing of Suspension subsystem | Improvement on Suspension Subsystem |  | Finalise design for suspension subsystem
| Administartive | [6 empty] | Doccumentation |  |  |  |  | Prepare doccumention and complile all results
Zac |  | Chassis Design |  |  |  |  | Fabrication of chassis |  | Assembly of chassis
|  |  | Design of Plate |  |  |  |  | Fabrication of Plate
|  |  | Motor Calculations | [6 empty] | Improve on suspension and chassis
Hilbert | Research | Secondary research on problem |  | CV Camera Research | [14 empty] | RESERVIST
| Navigation |  | ROS Installation and getting familiar |  | ROS Simulation on obstacle avoidance |  |  | Integrating UGV model into ROS Simulation | Mapping and Integrating to ROS Simulation | [11 empty] | Integrating ROS2 packages into physical UGV |  | Tuning and testing of UGV navigation
| UAV Communications |  |  |  |  | Communication research | Component Selection | Delivery of Components | Testing Communication between UGV and UAV computer | Simulation for communication link between UGV and UAV | [14 empty] | Integrating communication package with UAV
| Extras | Calculations for motor and components | [16 empty] | Designing final Chassis
| Report | [11 empty] | Prepare doccumention and complile all results | [17 empty] | Prepare doccumention and complile all results
Bryan |  |  | Component calculations and selection |  |  |  | Delivery of Components | Electrical Assembly/Soldering | [10 empty] | RESERVIST
[5 empty] | Wiring Diagram |  |  | Testing Power/Battery
[5 empty] | Communication chart and Power budget diagram |  |  | Programming of STM32
Testing Circuits
Gabriel |  | Yolo - CV |  |  |  |  | Delivery of Components | Electrical Assembly/Soldering
|  |  | Component calculations and selection |  |  |  | CV Data and Training
[5 empty] | Communication chart and Power budget diagram |  |  |  |  | Development of CV Proof of concept | [10 empty] | Integrating CV with ROS2 |  | Tuning and testing of UGV CV